## Sheet1
TIMELINE - 741 COL AVE: EBI (telecoms) + SHPO (state hist. pres. Office) + CP (consulting party Sue Peters)
| DATE | TIME | from EBI | to… | content | from SHPO | to … | content | from CP | to … | content
end of March
Sue gets 30-DAY DEADLINE of April 16, 2024 | 2024-04-03 | 13:12 PM | Green (EBI) | Sue(CP) cc Herter Boulough Brazee | Can you please have the comments submitted to EBI by the end of April 16, 2024? This would be 30 days from when I sent you the raw images of the balloon test. The SHPO has agreed to this date. Thank you for your diligence on this site and I will be more clear in my subject lines from now on.
| 2024-04-03 | 12:48 |  |  |  | Brazee | Sue(CP), cc Bullough Herter Green(EBI) | "Thank you, Susan. We have added your comments to our file."
Sue(CP) to SHPO re 30-DAY DEADLINE | 2024-04-02 | 15:13 | [6 empty] | Sue(CP) | Brazee, Bullough, cc Herter Green | "I hope you will understand my confusion about the applicable deadline, as I have received two further updates from CityBridgeLink5G @EBIconsulting.com , both declaring that the 30-day clock was starting."
| 2024-04-02 | 12:30 |  |  |  | Brazee | Sue(CP), cc Bullough Herter Green(EBI) | "Hello, Susan, The 30-day review period closed on 3/30, but please go ahead and submit your comments when ready. Thank you, ~Olivia"
Sue(CP) asks for 30-DAY DEADLINE | 2024-04-01 | [7 empty] | Sue(CP) | Bullough cc Brazee Herter Alexis(EBI) | "I am writing SHPO to confirm: what is the end date of the 30-DAY REVIEW PERIOD, for the site 741 Col Ave "
CityBridge to all CPs - 30-DAY CLOCK STARTS(???) | 2024-03-19 | 13:12 PM | CityBridge(Green EbI) | all CPs | RE: Addendum Submission / MN-07-120527_A / 30-DAY CLOCK STARTS / 741 Columbus Avenue, New York / EBI#6123006709 "Please see SHPO concurrence attached." [Following this email are the following two emails: (1) CityBridge to all CPs 3-15 11:29 am (2) CityBridge to all CP's 2/29 5:07 - see below. This is old 30-day advisory.] [Attachment: "SHPO concurrence 3-18". Here are emails found within attachment "SHPO concurrence 3-18": #1/ 3-18 5pm Herter "concur". #2/ 3-15 11:32 am Herter can access zip. #3/ 3-14 3:43 Green(EBI) to Herter, Bullough, Brazee "I had to pdf the images for E106...here is link to pages." #4/ 3-8 9:42 am Bullough to EBI, Brazee cc Herter "Happy to meet with you." #5/ 3-7 7:30 pm Green(EBI) to Bullough, Brazee cc Herter "appreciate opportunity to discuss"..."unclear how the finding has now been elevated to Adverse Effect" (5 bullet-point 'facts' follow from EBI) #6/ 3-7 2:14 Bullough = "Adverse Effect" #7/ 3-1 9:39 am "way to expedite? " #8/ 2-29 5:05 Green(EBI) to Brazee cc Herter Bullough "sending Sigma Tech Report" End Attachment: "SHPO concurrence 3-18"] NB: Following this email are the following emails: #1/ CityBridge to all CPs 3-15 11:29 am #2/ CityBridge to all CP's 2/29 5:07
CONCUR | 2024-03-18 | 17:00 |  |  |  | Herter | Green/EBI, Bullough/SHPO, Brazee/SHPO | 1. have reviewed 'additional raw footage' 2. rescind finding of 'Adverse Effect' 3. "only top portion of tower will be visible over existing one-story building" 4. "overall level of visibility will be minimal"
| 2024-03-15 | 11:32 |  |  |  | Herter/SHPO | Green/EBI, Bullough/SHPO, Brazee/SHPO | "Thank you. I was able to access the zip file."
CityBridge to CPs: 30-DAY CLOCK STARTS(???) | 2024-03-15 | 11:29 | CityBridge(Green EbI) | all CPs, including Sue(CP) | RE: Addendum Submission / MN-07-120527_A / 30-DAY CLOCK STARTS / 741 Columbus Avenue, New York / EBI#6123006709 "Please see the SHPO response to this project. In addition, SHPO verbally requested the raw images of the balloon test, which are linked below. link to raw.images.pdf. [Below this email is (1) another email - from 2/29 5:08 PM with 30-DAY-CLOCK STARTS message. This is old 30-day advisory.] [ATTACHMENT - file "SHPO Response 3-7-2024 pdf" (pdf contains 3 emails - #1 Bullough 3-7 2:17 Adverse Effect #2 Green(EBI) 3-1 9:39 ask SHPO to 'expedite' #3 Green(EBI) 2-29 5:05 to Brazee cc Herter, Bullough) EBI sends Sigma Technology report of 2/21 balloon shots)
TowerNotify | 2024-03-14 | 16:16 | Towernotifyinfo@fcc.gov | Sue(CP) | New document added to filing; date 3-14; doc type - photograph; doc description - raw images from mock up (SHPO-requested “balloon test” showing visibility from Central Park)
| 2024-03-14 | 15:43 | Green/EBI | Herter/SHPO, Bullough/SHPO, Brazee/SHPO | " link included in email to 'jpegs' of PDF images of "Line of Sight Test Raw images.zip"
| 2024-03-14 | 2:30:00 PM + | WHAT HAPPENED AT MEETING OF EBI & SHPO ? 3/14 @ 2:30 pm |  |  | WHAT HAPPENED AT MEETING OF EBI & SHPO ? 3/14 @ 2:30 pm
| DATE | TIME | from EBI | to… | content | from SHPO | to … | content | from CP | to … | content
SUE TO DO: enter dimensions of balloon structures: RICK what is actual width of canister? | 2024-03-14 | pics: afternoon Thurs. Sue alone with 4 new helium balloons on top of old balloon structure slowly deflating. | [6 empty] | Sue/CP | Rick | Sue created 4 helium balloons on top of deflating old balloon structure. Helium balloons were 26" wide. Sue indicated bottom of 13 feet from top with black lines on one of the balloons. Afternoon - sun on balloons and much less wind. Using scaffolding to secure balloons, Sue could see approximately 13 feet of white balloons from southeast corner of 97th St. and CPW. Pics: #11-14; #56, #59-60; #64-70; #75-79; #128-129; #133; #136; #142-143.
SUE TO DO: enter dimensions of balloon structures | 2024-03-13 | pics: afternoon, Wed. Sue alone with 13 foot balloon structure | [6 empty] | Sue/CP | Rick | Afternoon - sun on balloons to pick up whiteness of balloons, but still somewhat windy and hard to keep balloon structure above 1-story roof. Pics #29 and #68. Sue attached balloon structure to scaffolding.
SUE TO DO: enter dimensions of balloon structures | 2024-03-12 | pics: morning Tues. with Mike, holding 13-foot balloon structure | [6 empty] | Sue/CP | Rick | Sue and Mike (helper) meet balloon store at tower site. Store delivers balloon structure 13 feet tall and 28 inches wide (?). Some wind make it hard to raise balloon above 1-story bldg. to take pictures from CP. Also, workmen erecting scaffold in front of 1-story bldg., between kiosknyc and 1-story bldg. See pics #59 and #113.
| 2024-03-11 | pics: afternoon Mon. of tower on 118/Amsterdam | [6 empty] | Sue/CP | Rick | Sue takes pictures of cell tower at 118th St/Amsterdam: #25-27 whiteness; #28-30 white vs van; #32-33; #35
| DATE | TIME | from EBI | to… | content | from SHPO | to … | content | from CP | to … | content
| 2024-03-08 | 9:42 |  |  |  | Bullough | Green/EBI, Brazee/SHPO, cc: Herter/SHPO | "happy to meet. 3/14, 2:30pm"
| 2024-03-07 | 19:30 | Green/EBI | Bullough/SHPO, Brazee/SHPO, cc: Herter/SHPO | "possible to set up call with Bullough & Brazee?" "discuss how SHPO got Adverse Effect, considering especially these facts:"
1. 900 ft from Central Park (CP)
2. modern architecture in tower's immediate area; therefore, no historic preservation possibility
…therefore, should not be considered as part of setting of CP
…therefore, tower would not further compromise the surrounding area
3. pole visibility limited by a) mature trees b) large bldgs adjacent to park c) leaf off season - "only slightly visible" d) leaf on season - "next to no visibility"
4. CP is 840 acres in size; therefore, line of sight limited to small area of 1.43 acres [0.17% of entire park] [sue to rick - camel's nose under the tent]
5. balloons were white, more highly visible than "glossy and matte grey of proposed pole" [sue to rick - show pics of tower at 118/Amst with white top next to white truck]
| DATE | TIME | from EBI | to… | content | from SHPO | to … | content | from CP | to … | content
SUE TO CHECK | ON WHAT DATE DID I RECEIVE 3/7 ADVERSE EFFECT? |  | NB: Sue(CP) informed of SHPO's 3-7 retraction/new 'adverse effect' - ONLY ON 3-15 11:29 AM from CityBridge???? Why the delay???
SHPO: ADVERSE EFFECT | 2024-03-07 | 14:17 |  |  |  | Bullough | Green/EBI, Brazee; cc: Herter | 1. have reviewed 2/29 'visual analysis report' 2. top portion will be visible from HNL CP 3. considered viewshed impacts of tower on setting and design & light-colored and reflective materials 4. "distract from its special sense of place" 5. therefore adverse effect on NHL CP
Landmarks West! Updated comments | 2024-03-04 |  | Why was I not sent this new comment from Landmarks West -- I did not get a CityBridge memo with this info, and also any Towernotifyinfo@FCC.gov. Title of what I got as download from Chris Murray from EBI database: "UPDATED LW! Comments 3_4_24_741 COLUMBUS AVENUE - MN-07-120527_A" | [5 empty] | Landmarks West! | EBI database | Updated CP comments. 1) "proposed Link5G structure will be within an APE of historic properties and clearly visible from historic properties, namely Central Park." 2) "...Consulting Party comments then raised concerns about the effectiveness of the viewshed map EBI produced, backing up their claim that the proposed tower site would not be visible from Central Park." 3) "viewshed did not account for the deciduous nature of the trees" 4) "The view of the mockup, particularly views 2, 6, 7, 10, 11, 12, and 14, shows that there are considerable views from Central Park of the mockup/proposed site. Views 8 and 9 are blocked by temporary scaffolding and there is potential for further views from Central Park if this temporary scaffolding was not there." 5) "EBI notes the difference between the bright appearance of white balloons and an aluminum tower. We believe there is little difference in the brightness of white balloons and an aluminum tower. We would also like to stress that the real construction will not be the appearance of balloons floating in the air but a monumental 32 ft tall structure. This will be noticeable." 6) "We also question the 500 ft radius of APE that is being employed by EBI/Boldyn when visibility of proposed towers can impact properties outside of this APE threshold - especially a 32 ft tower on a sidewalk." 7) "We also believe that determining cumulative effect will not be wholly possible without seeing a manifest of the complete 5G rollout planned."
| 2024-03-01 | 9:39 | Green/EBI | Brazee; cc: Herter, Bullough | "Olivia, as this was a request for further information and that information was received rather quickly, 17 days, is there any way to expedite this with your office and the consulting parties? Lexi"
end of Feb
| 2024-02-29 | 17:16 | Towernotifyinfo@fcc.gov | Sue(CP) | New document - Email to SHPO re mock up 2.29.2024
EBI: 30 DAY PERIOD STARTS | 2024-02-29 | 17:08 | Green/EBI | all CPs | "30 DAY PERIOD STARTS; copy of submission packet for the site referenced in the subject line". New 30-day advisory attached.
| 2024-02-29 | 17:05 | Green/EBI | Brazee; cc: Herter, Bullough (SHPO) | "EBI contacted your office to get clarification on what the requested mockup should entail. Your office indicated that a balloon or balloons with the same width as the proposed pole and raised to the height of the proposed tower would be sufficient." EBI attaches Sigma Tech report of 2/21, with result of minimal visibility from boundary of CP. EBI says "No Effect" on Historic Resources within the Area of Potential Effects (APE)
| 2024-02-09 | 11:18 | Green(EBI) | CPs including Sue(CP) | RE: SHPO 5-DAY COMMENT SUMMARY FORM / 741 Col Ave; "Please find a copy of the form we are submitting to SHPO to alert them to the five-day review period at the close of the Consulting Party 30-day Review Period. I have appended the comments you have shared from your organizations. The SHPO will have until 2/14 to respond to the filing and the submitted comments." [ATTACHMENT: Sue's comments in response to SHPO Concurrence 1-10-2024]
Sue(CP) sends comments "Response to NYSHPO’s January 10, 2024 concurrence" | 2024-02-07 | 22:46 | [6 empty] | Sue (CP) | Brazee(SHPO), Green(EBI) | letter sent 10:46pm with Sue's CP comments attached; comments V4.4 titled: "Response to NYSHPO’s January 10, 2024 concurrence with finding of “No Effect”: 1. requests reconsideration and rescinding 2. proposed tower will be 34" wide or almost 3 feet in diameter; widest section is 13 3/4 feet from top and entire section will protrude above 1-story rooftop. 3. visibility maps (a) do not contain views from CP; (b) assume full-leaf only (c) omits map assumptions (4) assume 500 APE. V4.4 Includes timeline 12/30-1/10. Includes pic of tower in Chinatown.
| DATE | TIME | from EBI | to… | content | from SHPO | to … | content | from CP | to … | content
end of Jan
| 2024-01-12 | 20:56 | Green(EBI) | Sue(CP), Herter cc: Robinson/ Murray(EBI) Bullough Brazee | "All of the consulting parties have the standard 30 day review period as indicated in my previous emails. On day 31 the SHPO will then be provided all the consulting party comment with the Comment Summary Form per the Consulting Party Guide."
| 2024-01-12 | 20:04 | [6 empty] | Sue(CP) | Herter cc: Green(EBI) Murray(EBI) Bullough Brazee | "I am writing to express my concerns. The following is a timeline, which documents the important steps, which generated my concerns. It is very important that all Consulting Parties be allowed to respond, particularly because EBI provided entirely new exhbits that were NOT included in their Form 620 submission." SUE'S TIMELINE 1/8 3:56 pm thru 1/10 9:02 am
| 2024-01-11 | 11:46 | Towernotifyinfo@fcc.gov | Sue(CP) | New comment added - Text: SHPO concurrence received via email on 1/10/2024. Uploaded to CityBridge portal and sent to Consulting Parties via email on 1/11/2024. (EBI, CR)
| 2024-01-11 | 11:46 | Towernotifyinfo@fcc.gov | Sue(CP) | New document added - SHPO Concurrence 1.10.2024
CITYBRIDGE "106 consult now completed" | 2024-01-11 | 11:42 | Chris Robinson, arch(CITYBRIDGE) | CPs including Sue(CP) | MN-07-120527_A / SHPO 5-DAY COMMENT SUMMARY FORM / 741 Col Ave: "Consulting Parties – The SHPO has responded to the filing with concurrence and Section 106 consultation is now completed. Please let me know if you have any questions I can answer for you." ATTACHED: 6123006709 SHPO Concurrence 1.10.2024
SHPO: CONCUR | 2024-01-10 | 21:02 |  |  |  | Brazee | Green(EBI), Bullough; cc: Herter | "Thank you for the additional information/simulation- this is very helpful. The SHPO can concur with the finding of No Effect for this proposed location."
| 2024-01-09 | 15:51 | Green(EBI) | Brazee, Bullough; cc: Herter | EBI sends two more green viewshed photos; "In order to see the proposed pole from within Central Park at his location the person would need to be floating in the air approximately 16 stories up."
| 2024-01-09 | 15:00 |  |  | sends CPs' comments to SHPO | Brazee | EBI; Bullough; cc: Herter | "not clear there will be no visibility from CP, requests pics from NE corner of CP & CPW; want to be 100% certain no visibility from CP
| 2024-01-08 | 16:16 | Towernotifyinfo@fcc.gov | Sue(CP) | New document added: description = Email to the CPs regarding visibility info sent to SHPO
| 2024-01-08 | 16:16 | Towernotifyinfo@fcc.gov | Sue(CP) | New comment added - Text: Additional information regarding the potential visibility of the pole from the historic resources. Sent to the SHPO and Consulting Parties via email on January 8, 2024
| 2024-01-08 | 16:16 | Towernotifyinfo@fcc.gov | Sue(CP) | Visibility info sent to the SHPO 1.8.2024
| 2024-01-08 | 16:16 | Towernotifyinfo@fcc.gov | Sue(CP) | New Tower Submission Form
| 2024-01-08 | 15:56 |  | CPs (incl Sue) | sends added visibility analysis; 30 Day Review Starts
| 2024-01-08 | 15:42 | Green(EBI) | Bullough cc: Brazee | EBI: "500 APE mandated"; EBI sends 'viewshed/visibility map #1"
Y 2023 ENDS
end of Dec
SHPO retracts concurrence and asks for RELOCATION | 2024-12-30 | 16:04 |  |  |  | Bullough | Green(EBI) cc Brazee | "After reviewing the consulting party comments, we retract our concurrence and ask for a relocation, based on potential visibility from Central Park and some of the other historic resources cited by the consulting parties."
| 2024-12-29 | 16:16 | Towernotifyinfo@fcc.gov | peters.s@startmail.com | Please see uploaded comment summary form
| 2024-12-29 | 16:16 | Towernotifyinfo@fcc.gov | peters.s@startmail.com | Corrected ph# for Sue(CP)
| 2024-12-29 | 16:16 | Towernotifyinfo@fcc.gov | peters.s@startmail.com | Comment Summary Form 12-29
| 2024-12-29 | 16:16 | Towernotifyinfo@fcc.gov | peters.s@startmail.com | SHOP response 12/28
SHPO has until 1/8/2024 to respond. | 2024-12-29 | 14:19 | CityBridge | all CPs | "The SHPO has provided concurrence with EBI’s determination of “no effect on historic properties” on 12/28/2023, prior to EBI sending the Comment Summary Form. EBI has provided the SHPO with the summary form and your comments and will have until 1/8/2024 to respond." ( attachments to CPs: (attachment 1) CP Comment Period Summary Form: "no effect" from EBI along with comments from: HDC, LW!, NY Landmarks Conservancy, NY4WT(12-21-2023 from Sue); (attachment 2) 12-28-2023 7:06 pm Bullough to Green(EBI) "NYSHPO concurs with the recommended finding."
SHPO gets CP comments | 2024-12-29 | 14:11 | Green(EBI) | Bullough cc: Brazee | EBI sends CPs' comments to SHPO; NB: SHPO concurs 12/28 before receiving CPs comments
SHPO CONCURS with Applicant, before getting all CP comments | 2024-12-28 | 19:06 |  |  |  | Bullough | Green(EBI) | one sentence email: "SHPO concurs with recommended findings"
| 2024-12-27 | [6 empty] | transmittal memo
Sue's original CP comments | 2024-12-21 | 21-57 PM | [6 empty] | Sue(CP) | Green(EBI); uploaded by Murray to EBI db at 21:57pm | Sue original comments to SHPO, V.7, responding to applicant's Form 620: 1. applicant inaccurately asserts tower must be visible from nearest resource or "no adverse effect"; 2. applicant disregards "setting" along Col Ave, as character-defining feature to adjacent Historic District -- ornamental streetlight poles of historical significance of 9th Ave. El along Col Ave 3. applicant omits mention of multiple historically accurate reproduction streetlights and lamp poles in APE
| 2024-12-21 | map
| 2024-12-20 | map | [6 empty] | Sue(CP) | map | using Landmark West map, M&B poles between 88th St and 110th St -- added Historic Districts to map
| 2024-12-19 | pics 3pm+ | [6 empty] | Sue(CP) | pics | 106th St. to 90th St.; mostly B poles
| 2024-12-18 | map | [6 empty] | Sue(CP) | map | using Landmark West map, M&B poles between 88th St and 110th St
| 2024-12-12 | pics 3pm+ | [6 empty] | Sue(CP) | pics | from 88th St to 95 St.; M poles and B poles
| 2024-12-10 | pics 3pm+ | [6 empty] | Sue(CP) | pics | B poles in Riverside Park
| 2024-12-06 | 15:00 | EBI (Chris R, arch hist) | Sue (CP) | RE: 15-DAY REVIEW PERIOD STARTS; sent to my nychollis@
| 2024-12-06 |  | EBI | (not sent to Sue(CP) ) | FCC Form 620 with IDs of Consulting Parties; notification date 10-2-2023; site 741 Col Ave; Determination of effect: (1) Direct Effects: no historic properties in area of potential effects (APE); (2) Visual Effects: no effect on historic properties in APE; Historic Properties: have any historic properties been identified with the APEs for direct or visual effect? YES - UWS/CPWHD - no direct and no visual effect on this HP in APE. ATTACHMENTS: overhead photo with 500-foot APE and other street photos (all leaf-on summer)
p.49: Describe APE for direct effects: "limited to the pole installation area and underground utility easements."
p.49: Describe the APE for visual effects: "…the geographic area in which the Undertaking has the potential to introduce visual elements that diminish or alter the setting, including the landscape, where the setting is a character-defining feature of a historic property that makes it eligible for listing on the National Register."
p.49: Description of FCC's 2004 NPA's guidance for APE for visual effects…is the area from which the tower will be visible within a half mile from the tower site.
p.49: In consultation with the FCC, it has been determined that a 500-foot radius around the project site is an appropriate APE-VE for the vast majority of the CityBridge Link5G sites …. The area surrounding the project site shares the characteristics cited by the FCC so it has been determined that 500-feet is an appropriate radius for assessing the effects of the project on historic properties, if any exist.
p.49: Copies of any correspondence and summaries of any oral communications with the SHPO/THPO and any consulting parties. Answer: … no correspondence with the SHPO/THPO.
p.77: dimensions of tower: 19 feet from bottom to beginning of top canister; 13 feet length of top canister; total height = 32 feet 3 3/8 inches.
p97: Does the project site involve or is it substantially contiguous to a property listed or recommended for listing in the NY State or National Register of Historic Places? Answer: NO
| DATE | TIME | from EBI | to… | content | from SHPO | to … | content | from CP | to … | content
end of Nov
| 2024-11-30 | map | [6 empty] | Sue-map |  | B poles and M poles from 100th St to 93rd St
| 2024-12-27 | 15:17 | Towernotifyinfo@fcc.gov | peters.s@startmail.com | City Club Email and DC
| 2024-11-27 | 12:59 | EBI (Laino) | CP City Club of NY | to new CP, City Club of NY: 15-DAY REVIEW PERIOD STARTS
| 2024-11-26 | 4:00 pm + overcast - pics | [6 empty] | Sue's pics |  | M poles between 100 and 110 Streets on Columbus; at 110, 106 M, poles west and east on those blocks
| 2024-11-24 | 4:00 pm + pics | [6 empty] | Sue's pics |  | 1. mostly B poles between 97-92 - some leaves on ground from Nov trees 2. few M poles for traffic signals etc. 3. 1st draft of Sue's handwritten map of M poles 101 thru 94 sts.
| 2024-11-16 | 4:00 pm + pics | [6 empty] | Sue's pics |  | along 100-96 Sts and Columbus; Nov tree leaves; M lamp poles with 1. traffic signals (on pole or hanging off pole over traffic) 2. pedestrian signals on poles 3. directional signs on poles, etc.
| 2024-11-17 | 11:17 | Towernotifyinfo@fcc.gov | peters.s@startmail.com | new CP: City Club of NY
| 2024-11-15 | 15:16 | Towernotifyinfo@fcc.gov | peters.s@startmail.com | New Tower Submission Packet
| 2024-11-16 | 14:46 | Green(EBI) | peters.s@startmail.com | RE: 15-day review period starts now; sent to my wrong email. Error by EBI who made this email a CP for mCB7 directly (instead of New Yorkers For Wired Tech)
end of Oct
| 2024-10-20 | 7:00 | EBI's Chris Robinson, arch hist | CPs | FCC Form 620.
| 2024-10-19 | 11:46 | Towernotifyinfo@fcc.gov | EBI(Chris R, hist arch) | RE: Sec 106 New Filing Submitted PURPOSE: New Tower Submission Packet
| 2024-10-03 | 7:00 | EBI's Chris Robinson, arch hist | 5 CPs: HDC (Frampton), NY Landmark Conservancy, Preservation League of NY, Municipal Art Society, Landmark West! | FCC Form 620. RE: Initial Courtesy Notification - No Review Clock. "Per the FCC's guidance in Section of V.G of their 2004 NPA, as a consulting party, you are entitled to: (1) receive notices, copies of submission packets, correspondence and other documents provided to the SHPO/THPO in a Section 106 review; and (1) be provided an opportunity to have [your] views expressed and taken into account by the Applicant, the SHPO/THPO, and, where appropriate, by the Commission."